## JSON Export
id | name | duration | start_date | end_date
1 | Environment Available to WD (Ian Maxwell) [2022-01-18] | 0 | 2022-01-18 | 2022-01-18
2 | WD Deployment Testing (Welcom) [10 days, 2022-02-02] | 10 | 2022-01-19 | 2022-02-02
3 | WD Code Drop (Welcom) [3 days, 2022-02-08] | 3 | 2022-02-03 | 2022-02-08
4 | Smoke Testing (Carole Harley) [15 days, 2022-03-02] | 15 | 2022-02-09 | 2022-03-02
5 | System Testing (Carole Harley) [20 days, 2022-03-31] | 20 | 2022-03-03 | 2022-03-31
6 | User Acceptance Testing (including re-test) (Amanda Mills) [70 days, 2022-07-08] | 70 | 2022-04-01 | 2022-07-08
7 | Pre-Production Activities (Craig Baille) [20 days, 2022-08-08] | 20 | 2022-07-11 | 2022-08-08
8 | Go Live (Weekend) (ALL) [2022-08-09] | 0 | 2022-08-09 | 2022-08-09

## Plan
UUID From MSP Plan | Task Name | Visual Text | Duration | Start | Finish | Visual Flag | Owner | Visual Swimlane | Visual Track # Within Swimlane | Visual # Tracks To Cover | Format String | Done Format String | Text Layout
1 | Environment Available to WD | Environment Available to WD (Ian Maxwell) [2022-01-18] | 0 | 2022-01-18 | 2022-01-18 | TRUE | Ian Maxwell | Financier Upgrade Project | 2 |  | Milestone Dark Blue |  | Right
2 | WD Deployment Testing | WD Deployment Testing (Welcom) [10 days, 2022-02-02] | 10 | 2022-01-19 | 2022-02-02 | TRUE | Welcom | Financier Upgrade Project |  |  | Amber |  | Left
3 | WD Code Drop | WD Code Drop (Welcom) [3 days, 2022-02-08] | 3 | 2022-02-03 | 2022-02-08 | TRUE | Welcom | Financier Upgrade Project |  |  | Amber |  | Left
4 | Smoke Testing | Smoke Testing (Carole Harley) [15 days, 2022-03-02] | 15 | 2022-02-09 | 2022-03-02 | TRUE | Carole Harley | Financier Upgrade Project |  |  | Amber |  | Left
5 | System Testing | System Testing (Carole Harley) [20 days, 2022-03-31] | 20 | 2022-03-03 | 2022-03-31 | TRUE | Carole Harley | Financier Upgrade Project |  |  | Amber
6 | User Acceptance Testing (including re-test) | User Acceptance Testing (including re-test) (Amanda Mills) [70 days, 2022-07-08] | 70 | 2022-04-01 | 2022-07-08 | TRUE | Amanda Mills | Financier Upgrade Project |  |  | Amber
7 | Pre-Production Activities | Pre-Production Activities (Craig Baille) [20 days, 2022-08-08] | 20 | 2022-07-11 | 2022-08-08 | TRUE | Craig Baille | Financier Upgrade Project |  |  | Amber |  | Left
8 | Go Live (Weekend) | Go Live (Weekend) (ALL) [2022-08-09] | 0 | 2022-08-09 | 2022-08-09 | TRUE | ALL | Financier Upgrade Project |  |  | Milestone Dark Blue
Formulas:
Finish = WORKDAY(Table1[[#This Row],[Start]],Table1[[#This Row],[Duration]])
Start = WORKDAY([Finish, row above],1)